## Publishing timeline
Timing |  |  |  | 1 week | 1 week |  |  | 4 weeks |  | 2 weeks |  | 4 weeks | 2 week | 1 week | 1 week |  | 3 weeks
Chapter number | Chapter title | Author/s | First draft due | Copyright review due | Author edits due | Send to peer review 1 | Send to peer reviewer 2 | Return from peer reviewer 1 | Return from peer reviewer 2 | Author edits due | Send to copyeditor | Return from Copyeditor | Final edits due | Upload to PB | Final review due | Submit request to publish | Publication date
Note on D1: Works with multiple authors should review each others work and address inconsistencies with tone and structure. ---- @susie.phillips@monash.edu - Just wondering if this template would be clearer if we have a column for first draft due and another column for copyright review? Can we discuss? _Assigned to susie.phillips@monash.edu_ -Jenny Fafeita

## Further information
Further information
The Library team should be reviewing each chapter as they are submitted for copyright review. Check for glaring issues, accessibility concerns, basic formatting to make upload easier, consistency issues, etc.
The time periods for each stage are suggestions. These should be decided primarily by the authors. Communicate that changes to the timeline may have peer review and copyediting repercussions and should ideally be avoided.
In the case of large co-author projects, the team may decide to add another sheet to organise how who will proofread each chapter and by when.

## Copyright & attribution informa
"OER publishing schedule", by Monash University Library is licensed under CC BY NC 4.0